## Risk Register
Type | Title | Description | Project | Severity | Impact | Probability | Status | Owner | Category | Identified Date | Due Date | Last Review | Response | Trend
Threat | API rate-limit breach during peak traffic | Expected product launch surge may overwhelm third-party payment APIs. | Phoenix | Critical | Financial | High | Open | A. Nemeth | Technology | 2026-03-19 | 2026-05-20 | 2026-05-03 |  | Worsening
Threat | Unclear legal language in vendor addendum | Contract clause may expose liability on SLA penalties. | Atlas | High | Compliance | Medium | In Progress | M. Farkas | Legal | 2026-02-10 | 2026-04-30 | 2026-04-29 | Legal review and negotiated cap on penalties before signing. | Stable
Threat | Single-point failure in reporting ETL | Nightly pipeline has no parallel failover and delayed alerting. | Phoenix | Very High | Operational | High | Open | D. Kovacs | Operations | 2026-01-06 | 2026-06-10 | 2026-05-06 |  | Improving
Threat | Low sprint velocity due to key vacancy | One missing frontend engineer affects release commitments. | Nimbus | Medium | Schedule | Medium | Open | K. Szalai | People | 2026-04-01 | 2026-06-30 | 2026-05-08 |  | Stable
Threat | Dependency CVE in auth package | Newly published vulnerability affects currently deployed version. | Atlas | Critical | Security | Medium | Open | R. Molnar | Security | 2026-05-02 | 2026-05-16 | 2026-05-12 | Patch dependency, rotate secrets, and perform targeted penetration test. | Worsening
Threat | Legacy data migration quality issues | Null and malformed legacy records fail strict schema checks. | Orion | Medium | Data Quality | High | Mitigated | V. Toth | Data | 2025-12-14 | 2026-03-15 | 2026-04-20 | Pre-migration cleansing scripts and validation checkpoint in CI. | Improving
Threat | Cloud cost overrun from idle clusters | Night and weekend autoscaling floor is too high across regions. | Nimbus | Low | Financial | Medium | Open | B. Lakatos | FinOps | 2026-03-02 | 2026-07-01 | 2026-05-04 | Introduce schedule-based scaling and budget alerts. | Stable
Threat | Delayed stakeholder approvals | Sign-offs from external partners often miss the planned windows. | Orion | Low | Schedule | Low | Closed | E. Papp | Governance | 2025-11-20 | 2026-01-31 | 2026-02-01 | Introduced approval SLA dashboard and escalation path. | Improving
Opportunity | Early access to cloud volume discount tier | Projected spend trajectory qualifies for a reserved-instance discount negotiation window opening in Q3. | Nimbus | High | Financial | High | Open | B. Lakatos | FinOps | 2026-04-10 | 2026-07-15 | 2026-05-10 | Engage cloud account manager, model commitment tiers, and present business case to finance. | Improving
Opportunity | Strategic logistics partnership for Phoenix | A tier-1 logistics provider has expressed intent to co-market and integrate with the Phoenix platform. | Phoenix | Very High | Revenue | Medium | In Progress | A. Nemeth | Partnerships | 2026-03-25 | 2026-08-01 | 2026-05-15 | Assign partnership lead, draft MOU, and align product roadmap to integration requirements. | Improving
Opportunity | Regulatory simplification in key compliance area | Proposed amendment to data-residency rules could reduce Atlas compliance overhead significantly. | Atlas | Medium | Compliance | Low | Open | M. Farkas | Legal | 2026-02-28 | 2026-09-30 | 2026-04-18 | Monitor regulatory updates, engage legal counsel, and prepare architecture adaptation plan. | Stable
Opportunity | Open-source ETL library cuts pipeline build time | A recently released open-source framework covers 70% of Orion ETL patterns and is already battle-tested. | Orion | High | Schedule | High | Open | D. Kovacs | Technology | 2026-05-05 | 2026-06-20 | 2026-05-20 | Proof-of-concept sprint, security review of library, and incremental adoption plan. | Improving

## How To Fill
Caerus Risk Register - How To Fill
Quick Start
1) Enter one risk per row in the Risk Register sheet.
2) A unique Risk ID is generated automatically from the Title — keep titles descriptive.
3) Use consistent values for Severity, Probability, Status, and Trend.
4) Date fields must use YYYY-MM-DD format.
5) Fill Mitigation with concrete actions and next steps.
Field Definitions and Allowed Options
Field | Required | What to enter | Allowed options / examples
Type | No | Threat or Opportunity | Threat (default), Opportunity
Title | Yes | Short summary (ID auto-generated) | API outage during launch
Description | No | Details and context | What may happen and why
Project | Yes | Project or initiative name | Phoenix, Atlas, Orion, Nimbus
Severity | Yes | Consequence / benefit magnitude | Critical, Very High, High, Medium, Low
Impact | Yes | Primary area affected or benefited | Financial, Security, Compliance, Schedule, Revenue
Probability | No | Likelihood of occurrence | VeryHigh, High, Medium, Low, VeryLow
Status | No | Current state | Open, In Progress, Mitigated, Closed, Resolved
Owner | No | Accountable person | Initial + surname, or full name
Category | No | Domain | Technology, Security, Legal, Data, People, Operations
Identified Date | Yes | Date first identified | YYYY-MM-DD
Due Date | No | Target response date | YYYY-MM-DD
Last Review | No | Last review/checkpoint date | YYYY-MM-DD
Response | No | Planned response actions | Action-oriented and specific
Trend | No | Direction over time | Worsening, Stable, Improving
Severity Levels – Quick Guide
Level | Meaning | Example Scenario
Critical | Severe, potentially irreversible impact on operations, finances, or safety | Data breach exposing customer PII; complete production outage; regulatory shutdown order
Very High | Major impact affecting multiple teams or significant business functions | Key system down for several hours; contract penalty triggered; multi-week schedule slip
High | Significant impact on a team or business area requiring prompt attention | Single service degraded; compliance gap identified; sprint velocity drop >30%
Medium | Moderate impact, manageable within normal operations | Minor feature delay; minor cost overrun <5%; temporary workaround in place
Low | Negligible or cosmetic impact with little business consequence | Documentation gap; minor UI bug; low-urgency process inefficiency
Probability Levels – Quick Guide
Level | Meaning | Example Scenario
VeryHigh | Almost certain – expected to occur in most circumstances (>80%) | Known vulnerability actively exploited in the wild; vendor EOL already passed
High | Likely – will probably occur in many circumstances (60–80%) | Dependency upgrade overdue; stakeholder delays are a recurring pattern
Medium | Possible – might occur at some point (40–60%) | New regulation under consultation; third-party SLA borderline performance
Low | Unlikely – could occur but not expected (20–40%) | Rare edge-case failure mode; low-traffic integration with minor instability history
VeryLow | Rare – may occur only in exceptional circumstances (<20%) | Black-swan external event; theoretical attack vector with no known active exploits

## Highlights
Caerus Highlights
Quick Start
1) Add one highlight per row.
2) Date format: YYYY-MM-DD (optional but recommended).
3) Title is the only required field.
4) Project links the highlight to a specific project for filtering.
5) Body can contain multi-line narrative text.
Date | Title | Project | Body
2026-05-20 | Q2 Security Audit Passed | Atlas | Atlas completed its quarterly security audit with zero critical findings. All medium-severity items have remediation plans in place.
2026-05-12 | Auth CVE Patched Ahead of Schedule | Atlas | The auth package CVE was patched and deployed 4 days ahead of the due date. Secrets rotation completed with no service disruption.
2026-04-28 | Phoenix MVP Delivered On Time | Phoenix | The Phoenix minimum viable product was released to pilot customers on schedule. Initial feedback is positive with a 4.2/5 satisfaction score.
2026-04-05 | Orion ETL Reliability Up 18% | Orion | Following the active-passive failover implementation, the Orion reporting pipeline availability improved from 97.1% to 99.2% month-over-month.